EXHIBIT PROJECT TEAM & TIMELINE MANAGEMENT

Keep track of tasks involved in developing and fabricating your exhibit and assign SPECIFIC roles, responsibilities, and timelines.

| ROLES – many of these roles will be filled by the same person, but spread responsibility to team members as possible. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Project Manager: |  |  |  |  |  |  |  |  |  |  |
| CONTENT |  | Theme Development: |  |  |  |  | Content Review: |  |  |  |
|  |  | Research Objects: |  |  |  |  | Research Theme: |  |  |  |
|  |  | Label Writing: |  |  |  |  | Label Editing: |  |  |  |
| FABRICATION |  | Overall Exhibit Design: |  |  |  |  | Graphic Design: |  |  |  |
|  |  | Label Fabrication: |  |  |  |  | Construction: |  |  |  |
|  |  | Conservation Planning: |  |  |  |  | Object Mounts: |  |  |  |
|  |  | Installation: |  |  |  |  | Other: |  |  |  |
| EDUC |  | Education Materials: |  |  |  |  | Education Programming: |  |  |  |
|  |  | Evaluation: |  |  |  |  | Other: |  |  |  |
| RESPONSIBILITIES – note that these are existing workshop due dates, but fill in interim activities and own deadlines as needed. |  |  |  |  |  |  |  |  |  |  |
| # | Task |  |  | Owner | Helper(s) | Start |  | Due | Status | Notes |
| 1 | First draft of Exhibit Planning Worksheet (EPWS) outlining big idea, supporting concepts, initial object list (use form) |  |  |  |  |  |  | 11/13/23 |  |  |
| 2 | First draft of Project timeline & team roles (this document) |  |  |  |  |  |  | 11/13/23 |  |  |
| 3 | Object research (use form) |  |  |  |  |  |  | 1/8/24 |  |  |
| 4 | Topic research (use form) |  |  |  |  |  |  | 1/8/24 |  |  |
| 5 | Update EPWS based on research |  |  |  |  |  |  | 1/8/24 |  |  |
| 6 | Sketch exhibit layout plan |  |  |  |  |  |  | 2/12/24 |  |  |
| 7 | Plan for safe object display |  |  |  |  |  |  | 2/12/24 |  |  |
| 8 | Update EPWS based on space and object considerations |  |  |  |  |  |  | 2/12/24 |  |  |
| 9 | Compile research into rough outline (use form) |  |  |  |  |  |  | 3/11/24 |  |  |
| 10 | Draft labels (use form) |  |  |  |  |  |  | 3/11/24 |  |  |
| 11 | Update EPWS based on rough outline and label decisions |  |  |  |  |  |  | 3/11/24 |  |  |
| 12 | Draft Education Self-Guide |  |  |  |  |  |  | 4/8/24 |  |  |
| 13 | Draft Education Plan |  |  |  |  |  |  | 4/8/24 |  |  |
| 14 | Finalize EPWS |  |  |  |  |  |  | 4/8/24 |  |  |
| 15 | Build mounts & prepare case |  |  |  |  |  |  | 5/6/24 |  |  |
| 17 | Design & create labels |  |  |  |  |  |  | 5/6/24 |  |  |
| 18 | Install prototype exhibit |  |  |  |  |  |  | 5/6/24 |  |  |
| 19 | Create visitor survey (use form) |  |  |  |  |  |  | 5/6/247 |  |  |
| 20 | Revise & finalize from feedback |  |  |  |  |  |  | 7/1/24 |  |  |
| 21 | Final report due to UH |  |  |  |  |  |  | 8/1/24 |  |  |